## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E012B |  | Project Name: |  | 98th & Sage Storage Frontera
NPDES Id. No. | NMR10066R |  | Location: |  | 9850 De Vargas Rd SW
2024-06-17 |  | Owner |  |  |  | Contractor
Operator |  | FRE Albuquerque SS, LLC
Contact name & title |  | Brian Grissinger & Todd Megrath |  |  |  | David Harvey & lan Ring
e-mail |  | bryan@fronteerarearealestate.com |  |  |  | 913902
Contact Phone # |  | 619-756-4622 |  |  |  | 913-302-7409
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11:30AM |  |  |  | Rain
Construction Phase: |  | verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - Dirt is more than half the height of the SiltFence on the east side of the site, halfway between the pond and the stabilized exit. Required Mitigation: Ensure that all stormwater controls (BMPs) are maintained and remain in effective operating condition during permit coverage per CGP 2.1.4. If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day per CGP 2.1.4.b. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational or complete the repair by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
SWPPP is located in the Conex.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action