## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E025A |  | Project Name: |  | Sage Ranch Subdivision
NPDES Id. No. | NMR1004GM |  | Location: |  | 9600 Sage Ranch Ct. NW | [5 empty] | brian@abrazohomes.com
2023-12-28 |  | Owner |  |  |  | Contractor
Operator |  | Sage Ranch , LLC |  |  |  | Westway Homes |  |  |  |  | ck@abrazohomes.com
Contact name & title |  | Mike Feetz |  |  |  | Mike Feetz
e-mail |  | mike@thewestway.com |  |  |  | mike@thewestway.com
Contact Phone # |  | 379-5368 |  |  |  | 379-5368
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10am |  |  |  | Rain
Construction Phase: |  | House Construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-12-23 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | 1. The SWPPP map wasn’t up-to-date, because it didn’t identify the lots where construction was complete, BMPs had been removed, and the lots had been transferred to the new homeowner. The first informal notice of a SWPPP violation was emailed to you on 1/27/2022 and the second on 11/30/23. Required Mitigation: The SWPPP, including the SWPPP map, Self Inspection Reports and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3.
2 | Sediment was present in the street and had not been removed in violation of CGP 2.2.4.d. Required mitigation: Where sediment has been tracked-out from your site onto paved roads and sidewalks remove the deposited sediment by the end of the same business day CGP 2.2.4.d.
3 | Washout - Concrete washout was on the ground on lot 29. Required Mitigation: Remove and dispose contaminated soils and hardened concrete with other waste in per CGP 2.2.3. Direct all future wash water from concrete, paint, and stucco into a leak-proof container per CGP 2.3.4
4 | Waste - The waste container open during the inspection on 12/28/23 and while it was raining on 1/4/24 when no personel were present either time.
5 | The Porta Potty wasn't supported.
6
| Discharge off site? (Y/N) |  |  | no | [6 empty] | No
| Self Inspection Reports |  |  | OK | Latest report Date: |  | 2023-12-28
Notes:
The property owner is Sage Ranch LLC according to Bernalillo County records, but the NOI is in the name of the contractor, Westway Homes both at the same address with Mike Fietz being the principal of both. The SWPPP is in the lockbox on back of the sign. We weren't able to confirm a continuous record of self-inspection, paper copies stoped on 1/1/21 and digital copies began on 11/02/23.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 505- 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action