## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [9 empty] | 1001 De Vargas Rd.
ESC File No. | M09E030 |  | Project Name: |  | Westgate Community Center |  |  |  |  | 505-768-3827
NPDES Id. No. | NMR10030Y |  | Location: |  | 1001 De Vargas Rd. |  |  |  |  | Sherry Keefe
2021-05-25 |  | Owner |  |  |  | Contractor
Operator |  | City of Albuquerque |  |  |  | Bradbury Stamm |  |  |  | Tim Slatunas
Contact name & title |  | Sherry Keefe |  |  |  | Tim Tolbert
e-mail |  | skeefe@cabq.gov |  |  |  | ttolbert@bradburystamm.com
Contact Phone # |  | 505-768-3827 |  |  |  | 505-264-8318
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 10:50 AM/11:15 AM |  |  |  | Rain
Construction Phase: |  | Building construction/landscaping | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 74 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | No posting of NOI permit coverage. Post signage of permit coverage in a location clearly visible to the public. | [8 empty] | 2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action