## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Solare Collegiate Charter School Phase 3
Location: |  |  | Gibson and Barbados
Site Contact Name & Agency |  |  | Rachel Sewards |  |  |  | ESC File No. | M09E031
|  |  | Solare Collegiate Foundation |  |  |  | NPDES Id. No. | own NMR10026S & NMR10026D Contr
Inspection Date: |  |  | 2024-12-05 | Start/End Time: |  | 9:20am |  | returned |  | 11:15am
CoA Stormwater Inspector: |  |  |  | Doug Hughes | [9 empty] | Rain
Construction Phase: |  |  | grading | [10 empty] | Clear/ Windy
Type of Inspection: |  | X | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2020-12-11 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Silt fence must be reset.
2 | Provide updated SWPPP Map with additional controls at stockpile.
3 | Provide updated NOI (New end date and area).
4 | Provide plan showing final stabelization for all disturbed area.
5 | Provide schedule/sequence of construction w/ phases, final stabelization, and removal of BMPs.
6 | Provide latest self inspection report
7 | Stabelize Gibson blvd. at trail
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date: |  | 2020-01-03
Notes:
New pad graded west of parking lot and new dirt moved to stockpile.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Doug Hughes 924-3420
|  |  | jhughes@cabq.gov |  |  |  |  | 2024-12-05

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action