## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Solare Collegiate Charter School
Location: |  |  | Gibson and Barbados
Site Contact Name & Agency |  |  | Rachel Sewards |  |  |  | ESC File No. | M09E031
|  |  | Solare Collegiate Foundation |  |  |  | NPDES Id. No. | NMR10026S
Inspection Date: |  |  | 2019-06-11 | Start/End Time: |  | 8:45/8:50 |  | returned | 9:40/10:00
CoA Stormwater Inspector: |  |  |  | Curtis Cherne | [8 empty] | Rain
Construction Phase: |  |  | grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | X | Regular |  | Storm Event |  | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2019-05-10 |  |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Site not posted
2 | No vechicle tracking control (track-out) pad
3 | minor track-out across cattle guard drain
4 | Vehicle tracking control in wrong location
5 | dirt ramp constructed in Barbados St.
6 | sediment in gutter on Barbados St. May be related to installation of the silt fence
7 | No inlet protection
8 | silt fence not buried along east edge in multiple locations for a total of approx 120 feet
9 | sediment pile on Gibson Blvd 5 feet uphill from drain. May be related to the installation of the silt fc.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [6 empty] | No
4 | Self Inspection Reports | [5 empty] | Latest report Date:
Notes:
silt fence was installed around perimeter of site
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Curtis Cherne PE, 505-924-3420
|  |  | ccherne@cabq.gov |  |  |  |  | 2019-06-11

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action