## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E032 |  | Project Name: |  | Sombra del Oeste
NPDES Id. No. | NMR1005WH |  | Location: |  | Gibson Blvd and Valley Cottonwood SW
2025-06-27 |  | Owner |  |  |  | Contractor
Operator |  | Homewise Inc. |  |  |  | Shane
Contact name & title |  | Eugene Chavez |  |  |  | Shane Meihaus
e-mail |  | echavez@homewise.org |  |  |  | shane@compassnm.com
Contact Phone # |  | 505-983-9473 |  |  |  | 505-221-6003
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | Curbs, prep for paving | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-25 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP and self inspection reports need to be certified by Homewise, Inc. in violation of CGP Parts 4.7.2 and 7.2.10. Required mitigation: Your signatory must sign and date the SWPPP and each inspection report in accordance with CGP Appendix G, Part G.11 according to CGP Parts 4.7.2 and 7.2.10.
| Discharge off site? (Y/N) |  |  | No | [6 empty] | No
| Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-06-18
Notes:
The SWPPP is located in a box on a pole at the eastern entrance. The posting is near the western entrance. Previous violations have been mitgated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chanacellor English 505-294-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action