## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E032 |  | Project Name: |  | Sombra del Oeste
NPDES Id. No. | NMR1005WH |  | Location: |  | Gibson Blvd and Valley Cottonwood SW
2025-10-15 |  | Owner |  |  |  | Contractor
Operator |  | Homewise Inc. |  |  |  | Shane
Contact name & title |  | Eugene Chavez |  |  |  | Shane Meihaus
e-mail |  | echavez@homewise.org |  |  |  | shane@compassnm.com
Contact Phone # |  | 505-983-9473 |  |  |  | 505-221-6003
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | Curbs, prep for paving | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP and self inspection reports need to be certified by Homewise, Inc. in violation of CGP Parts 4.7.2 and 7.2.10. Required mitigation: Your signatory must sign and date the SWPPP and each inspection report in accordance with CGP Appendix G, Part G.11 according to CGP Parts 4.7.2 and 7.2.10.
2 | The posting was moved and not reposted where it is in public view in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site.
| Discharge off site? (Y/N) |  |  | No | [6 empty] | No
| Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-10-08
Notes:
The posting and SWPPP were found on ground by the wall running along Gibson Blvd. Mount the Permit Coverage posting where it can be viewed from a public right-of way.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chanacellor English 505-294-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action