## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E035 |  | Project Name: |  | Take 5 Car Wash Snow Vista
NPDES Id. No. | NMR1005E4 |  | Location: |  | 98th & Sage
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | Boing US Holdco, Inc. |  |  |  | Spinoff Construction
Contact name & title |  | Jorge Primo Planta |  |  |  | Jimmy Gibson
e-mail |  | jorge.planta@drivenbrands.com
Contact Phone # |  | 919-699-7198 |  |  |  | 832-654-8008
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-11-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The site supervisor did not have a key to the construction office and was unable to produce the SWPPP or inspection reports in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | The perimeter silt fence has gaps and sags and needs maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Temporary site supervisor was not given a key to the construction office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action