## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E035 |  | Project Name: |  | Take 5 Car Wash Snow Vista
NPDES Id. No. | NMR1005E4 |  | Location: |  | 98th & Sage
2025-05-20 |  | Owner |  |  |  | Contractor
Operator |  | Boing US Holdco, Inc. |  |  |  | Spinoff Construction
Contact name & title |  | Jorge Primo Planta |  |  |  | Jimmy Gibson
e-mail |  | jorge.planta@drivenbrands.com |  |  |  | jgibson@spinoffconstruction.com
Contact Phone # |  | 919-699-7198 |  |  |  | 832-654-8008
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | verticals, grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were seen in the office, but the office was locked, and the superintendent was not on-site to unlock the office at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the SWPPP and copies of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | The construction entrance needs maintenance as vehicles are cutting the corner which makes sediment track-out a concern in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2024-03-18
Notes:
SWPPP is in office of car wash. The superintendent was absent and the office was locked.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action