## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR1003NO
ESC File No. | M10E020 |  | Project Name: |  | Kidz Academy and The Human Bean | [5 empty] | Kidz Academy Preschool and The Human Bean; 7800 Sage Rd. SW
NPDES Id. No. | NMR1003NO/NMR1003NP |  | Location: |  | 7800 Sage Rd. SW | [5 empty] | Kidz Academy Preschool Ladera Real Estate LLC; Keith Griego |  | Raymond Herrera
2022-01-26 |  | Owner |  |  |  | Contractor |  |  |  |  | 505-681-7812 |  | 505-410-9020
Operator |  | Kidz Academy and Tres Lobos |  |  |  | Creative Design Builders |  |  |  |  | kidzacademystaff@gmail.com |  | rhcdb46@yahoo.com
Contact name & title |  | Keith Griego |  |  |  | Raymond Herrera
e-mail |  | kidzacademystaff@gmail.com |  |  |  | rhcdb46@yahoo.com
Contact Phone # |  | 505-681-7812 |  |  |  | 505-410-9020 |  |  |  |  | Inspections Plus
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4pm |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-01-01 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Inlet Protection in Sage downstream of the site is not maintained and and there is too much sediment in the street upstream of the inlet. Sediment must be removed from Sage and from the parking lot east of Kidz Academy and the inlet protection reset. | [9 empty] | 2021-05-03
2 | Silt fence is missing. The areas of disturbance south of the site, both onsite and on the adjacent property must either have silt fence or final stabilization, and the debris removed in a covered waste container. | [9 empty] | 2021-05-31
3 | The SWPPP wasn't available and its location wasn't identified on the sign because the sign was missing. Last inspection - 1) Reports were not signed by Operators or Delegated Authority 2)swq team not per CGP 6.1. The SWPPP mis be u-to-date including the map, and be accessable onsite, its location posted.
4 | Posting of NPDES Permit coverage was missing and must be posted for safe public viewing for all three operators.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | ? | Latest report Date: |  | ?
Notes:
Human bean looked like it is open for business but signs missing, Kidz academy is nearly complete. Incomplete stabilization, lack of posting, sediment, and missing BMPs must be mitigated. Raymond said he couldn't get it all done by Monday so an extra week is being allowed.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 505 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action