## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E008 |  | Project Name: |  | Wagoner Building
NPDES Id. No. | NMR1005TB/NMR1005TC |  | Location: |  | 1800 Randolph Rd SE
2025-05-28 |  | Owner |  |  |  | Contractor
Operator |  | LOE Investments LLC |  |  |  | Eastley Inc.
Contact name & title |  | Matt Wagoner |  |  |  | Matt Wagoner
e-mail |  | matt@eastleyinc.com |  |  |  | matt@eastleyinc.com
Contact Phone # |  | 951-712-1394 |  |  |  | 951-712-1394
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:45am |  |  |  | Rain
Construction Phase: |  | Foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Posting - CGP coverage was not posted so it is visible from the public right-of-way in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way.
2 | SWPPP - The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and a copy of all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. If an on-site location is unavailable to keep the SWPPP and self-inspection reports when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site.
3 | BMPs - The silt fence on the northeast corner has been taken down and needs to be re-installed in violation of CGP Part 2.1.2. Required mitigation: Design and install all stormwater controls in accordance with good engineering practices, including applicable design specifications per CGP Part 2.1.2.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action