## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E021A |  | Project Name: |  | Whataburger - Albuquerque
NPDES Id. No. | NMR1006PS |  | Location: |  | 2060 Gibson Blvd SE
2025-09-23 |  | Owner |  |  |  | Contractor
Operator |  | Whataburger Restaurants LLC
Contact name & title |  | James Turcotte
e-mail |  | harcher@wbhq.com
Contact Phone # |  | 210-665-0098
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-09-14 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Posting - There was no posting of your permit coverage in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enouch to be readily viewed from a public right-of-way.
2 | SWPPP - The SWPPP and inspection reports were not located in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site.
3 | BMPs - The designed stabilized construction entrance has not been installed in violation of CGP Part 2.1.3. Required mitigation: Complete installation of stormwater controls by the time each phase of construction activities begin per CGP Part 2.1.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The gates were locked, and there was no personnel on-site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action