## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E021A |  | Project Name: |  | Whataburger - Albuquerque
NPDES Id. No. | NMR1006PS |  | Location: |  | 2060 Gibson Blvd SE
2025-01-12 |  | Owner |  |  |  | Contractor
Operator |  | Whataburger Restaurants LLC
Contact name & title |  | James Turcotte
e-mail |  | harcher@wbhq.com
Contact Phone # |  | 210-665-0098
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Posting - There was no posting of your permit coverage in violation of CGP Part 1.5. QR codes are not acceptable as a posting. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enouch to be readily viewed from a public right-of-way.
2 | SWPPP - The self-inspection reports were not available "same as paper" during the inspection in violation of CGP Part 4.7.3. Multiple requirements were missing from the SWPPP: Identification of the Stormwater Team by name and position, along with their responsibilities and training (CGP Part 7.2.2) and the NOIs for each operator (CGP Part 7.2.11).
3 | Washout - There is concrete washout on bare ground in violation of CGP Part 2.3.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The SWPPP is in the mobile construction office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action