## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E021B |  | Project Name: |  | Mister Car Wash #1394
NPDES Id. No. | NMR100506 |  | Location: |  | 2161 Gibson Blvd SE
2023-09-06 |  | Owner |  |  |  | Contractor
Operator |  | CWPS Corp, a Delaware Corporation |  |  |  | Texana Builders
Contact name & title |  | Prabhs Matharoo |  |  |  | Damian Toth
e-mail |  | pmatharoo@mistercarwash.com |  |  |  | damian@texanabuilders.com
Contact Phone # |  | 520-615-4000 |  |  |  | 832-704-8484
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | vertical, grading, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Certification signatures are missing in the SWPPP according to CGP Appendix G, Part G.11.2. The SWPPP map is out-of-date in violation of CGP Part 7.4.1. Required mitigation: CGP Appendix G, Part G.11.2 states that the SWPPP, any SWPPP modifications, inspection reports, corrective actions, and other compliance documentation must be signed by the operators or a duly authorized representative. An individual is a duly authorized representative if the authorization is made in writing (signed, dated, and included in the SWPPP) by the operators and the authorization specifies either an individual or a position having responsibility for the overall operation of the facility, such as the on-site superintendent. (Note: the duly authorized representative cannot be a subcontractor or third-party.) You must modify your SWPPP within 7 days whenever you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP as per CGP Part 7.4.1.
2 | There was sediment trackout on the access road and along Miles Rd to the south of the property by vehicles still using an old construction entrance on the southwest corner with no controls in violation of CGP Part 2.2.4. Required mitigation: You must restrict vehicle use to properly designated exit points and use appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4. This Part also requires that sediment that has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site be removed by the end of the same business day in which the track-out occurs and to remove by sweeping, shoveling, or vacuuming.
3 | Concrete washout was found adjacent to the perimeter silt fence in violation of 2.3.4. Required mitigation: You must direct washwater into a leak-proof container or leak-proof and lined pit and do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground as per CGP Part 2.3.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | NA
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action