## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E021C |  | Project Name: |  | Dutch Bros. NM0303
NPDES Id. No. | NMR1005GM |  | Location: |  | 2131 Gibson Blvd SE
2023-09-06 |  | Owner |  |  |  | Contractor
Operator |  | Dutch Bros, LLC
Contact name & title |  | Daniel Batty
e-mail |  | daniel.batty@dutchbros.com
Contact Phone # |  | 541-955-4700
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 330pm |  |  |  | Rain
Construction Phase: |  | Gradin, foundation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | There was no permit coverage posting located at or near the site. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site, and the notice must be located so it is visible from the public road that is nearest to the active part of the construction site per CGP Part 1.5.
2 | The SWPPP and self-inspection reports were not available at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and a copy of all inspection reports at the site or at an easily accesible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
3 | At the time of the inspection, the BMP installations were not complete before land disturbing activities had been initiated. The perimeter silt fence was not complete and the contruction entrance was not yet installed while excavation was in process in violation of CGP Parts 2.1.3, 2.2.3, and 2.2.4. Required mitigation: You must complete the installation of stormwater controls by the time each phase of construction has begun per CGP Part 2.1.3. Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3. You must minimize sediment track-out by restricting vehicle use to designated exit points and use appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | NA
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action