## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E021F |  | Project Name: |  | Panda Express
NPDES Id. No. | None |  | Location: |  | 2040 Gibson Blvd SE
2025-02-13 |  | Owner Lot C-2 |  |  |  | Owner Lot C-1
Operator |  | CFT NV Developments, LLC |  |  |  | I25 & Gibson LLC
Contact name & title |  | Derek Knight |  |  |  | Wes Butero
e-mail |  | derek.knight@pandarg.com |  |  |  | wes@mdgrealestate.com
Contact Phone # |  | 626-799-9898 |  |  |  | 505-228-2149
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | Utilities, foundation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | NOI - Construction activity has started before City SWQ Approval, the City has no NOI or ESC Plan on record in violation of City Ordinance §14-5-2-11. Required mitigation: For projects that disturb one acre or more, or less than one acre but are part of a common plan of development exceeding one acre, the property owner is to provide the CGP Notice of Intent documentation that contains the property owner name and contact information a minimum of 14 days prior to earth disturbance and prior to obtaining Work Order or Building Permit approval per City Ordinance §14-5-2-11(A).
2 | Posting - Permit postage coverage was missing from the site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP Part 1.5.
3 | SWPPP - The SWPPP and self-inspection reports were unavailable during the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all copies of inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
4 | BMPs - A stockpile on the pavement of the neighboring property (Lot C-1) has no stormwater controls to prevent being washed into the City's curb and gutter storm system in violation of CGP Parts 2.1.3 and 2.2.3. Required mitigation: Complete installation of stormwater controls by the time each phase of construction activities has begun per CGP Part 2.1.3. By the time construction activity in any given portion of the site begins, install and make operational any downgradient sediment controls that control discharges from the initial site clearing, grading, excavation, and other earth-disturbing activities. Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action