## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E021F |  | Project Name: |  | Panda Express
NPDES Id. No. | NMR100738 |  | Location: |  | 2040 Gibson Blvd SE
2025-03-28 |  | Owner |  |  |  | Operator
Operator |  | CFT NV Developments, LLC |  |  |  | Johansen Interiors
Contact name & title |  | David Luo |  |  |  | Jeff Johansen
e-mail |  | david.luo@cherngFT.com |  |  |  | jeff@johanseninteriors.com
Contact Phone # |  | 626-372-8526 |  |  |  | 480-907-5986
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9am |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | All operators need to certify the SWPPP correctly (A signed Delegation of Authority is acceptable for the delegation to sign the SWPPP for the individuals above). Ron Silverstein has signed for the owner but has no Delegation of Authority included in the SWPPP. The contractor also needs to sign the certification for the SWPPP. (CGP Part 7.2.10 and CGP Appendix G, Part G.11.2)
2 | The members of the stormwater team have not been identified by name and position in the SWPPP. The stormwater team consists of persons responsible for a) the design of BMPs, b) the installation of BMPs, c) the maintenance and repair of BMPs, d) chemical storage (if applicable), e)corrective actions, and f) inspections. (CGP Parts 6 and 7.2.2)
3 | All inspection reports need to be certified and signed by all operators or their delegated authorities (CFT NV Developments, LLC and Johansen Interiors). (CGP Part 4.7.2)
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-03-20
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action