## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E023B |  | Project Name: |  | Avid Hotel
NPDES Id. No. | NMR1006J0 & 6IR |  | Location: |  | 1441 Woodward Rd. SE | [5 empty] | kwechter@pacventures.com
2025-01-22 |  | Owner |  |  |  | Contractor
Operator |  | 1441 Sunport, LLC |  |  |  | HEI Construction, LLC |  |  |  |  | Tim@greenglobenm.com
Contact name & title |  | R-Nicholas Eveleigh |  |  |  | Yogash Kumar
e-mail |  | heiconstruction@yahoo.com & rne@hmsgallup.com |  |  |  | yogash@hmsgallup.com |  |  |  |  | heiconstruction@yahoo.com | rne
Contact Phone # |  | 505-339-6201 |  |  |  | 505-879-7613
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  |  | Rain
Construction Phase: |  | Verticals | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 40 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Posting - CGP coverage was not posted so it is visible from the public right-of-way in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way.
2 | SWPPP - The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and a copy of all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. If an on-site location is unavailable to keep the SWPPP and self-inspection reports when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site.
2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The previous violations (Waste, Washout, BMPs) have been mitigated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action