## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E023B |  | Project Name: |  | Avid Hotel
NPDES Id. No. | NMR1006J0 & 6IR |  | Location: |  | 1441 Woodward Rd. SE | [5 empty] | kwechter@pacventures.com
2025-05-28 |  | Owner |  |  |  | Contractor
Operator |  | 1441 Sunport, LLC |  |  |  | HEI Construction, LLC |  |  |  |  | Tim@greenglobenm.com
Contact name & title |  | R-Nicholas Eveleigh |  |  |  | Yogash Kumar
e-mail |  | heiconstruction@yahoo.com & rne@hmsgallup.com |  |  |  | yogash@hmsgallup.com |  |  |  |  | heiconstruction@yahoo.com | rne
Contact Phone # |  | 505-339-6201 |  |  |  | 505-879-7613
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  |  | Rain
Construction Phase: |  | Verticals | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 85 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2025-05-04 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The self-inspection reports were not up-to-date in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-04-17
Notes:
The previous violations (Waste, Washout, BMPs) have been mitigated.
The new concrete entrance onto Flightway Ave. (north side of site) is a discharge point and needs to be protected from any sediment discharges.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action