## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E023B |  | Project Name: |  | Avid Hotel
NPDES Id. No. | NMR1006J0 & 6IR |  | Location: |  | 1441 Woodward Rd. SE | [5 empty] | kwechter@pacventures.com
2026-01-22 |  | Owner |  |  |  | Contractor
Operator |  | 1441 Sunport, LLC |  |  |  | HEI Construction, LLC |  |  |  |  | Tim@greenglobenm.com
Contact name & title |  | R-Nicholas Eveleigh |  |  |  | Yogash Kumar
e-mail |  | heiconstruction@yahoo.com & rne@hmsgallup.com |  |  |  | yogash@hmsgallup.com |  |  |  |  | heiconstruction@yahoo.com | rne
Contact Phone # |  | 505-339-6201 |  |  |  | 505-879-7613
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  |  | Rain
Construction Phase: |  | Verticals | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 50 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2026-01-08 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Washout - There is concrete or stucco washout on bare soil running off into the construction exit in violation of CGP Part 2.3.4. Required mitigation: Direct wash water to a leak-proof container or a leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2026-01-08
Notes:
The previous violations have been mitigated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action