## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E023B |  | Project Name: |  | Avid Hotel
NPDES Id. No. | NMR1004TD |  | Location: |  | 1441 Woodward Rd. SE | [5 empty] | kwechter@pacventures.com
2022-06-16 |  | Owner |  |  |  | Contractor
Operator |  | Sunport Lodging LLC | [8 empty] | Tim@greenglobenm.com
Contact name & title |  | Vinohd Perumal
e-mail |  | Vinodh@vetrimgt.com
Contact Phone # |  | 879-7168
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:30am |  |  |  | Rain
Construction Phase: |  | Paved, near closeout | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-06-19 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none | [9 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | not active | Latest report Date: |  | n/a
Notes: | Plan review still in progress, G&D Plan not even submited yet.
Light gravel over disturbed site provides borderline cover, assumed to be adequate.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action