## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E023B |  | Project Name: |  | Avid Hotel
NPDES Id. No. | NMR1006J0 & 6IR |  | Location: |  | 1441 Woodward Rd. SE | [5 empty] | kwechter@pacventures.com
2024-06-30 |  | Owner |  |  |  | Contractor
Operator |  | 1441 Sunport, LLC |  |  |  | HEI Construction, LLC |  |  |  |  | Tim@greenglobenm.com
Contact name & title |  | Yogash Kumar & R-Nicholas Eveleigh
e-mail |  | heiconstruction@yahoo.com & rne@hmsgallup.com |  |  |  | yogash@hmsgallup.com |  |  |  |  | heiconstruction@yahoo.com | rne
Contact Phone # |  | 879-7168 |  |  |  | 879-7613
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:30am |  |  |  |  | Rain
Construction Phase: |  | Paved, near closeout | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-06-29 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | BMPs—The silt fence in the NW corner of the site failed because it was not designed and installed according to good engineering practices, in violation of CGP 2.1.2. It receives concentrated flow because it isn't installed on contour. Required mitigation: Redesign and reinstall the stormwater controls in the NW corner of the site in accordance with good engineering practices, including applicable design specifications. | [9 empty] | 2021-05-03
2 | Sediment - Stormwater from this site caused severe erosion on this site and downstream, resulting in a significant portion of the sediment deposition at the bottom of the hill in Flightway Ave. Required Mitigation: Where sediment has been discharged from your site onto paved roads and sidewalks, remove the deposited sediment by the end of the same business day. Remove the sediment by sweeping, shoveling, or vacuuming these surfaces or using other similarly effective means of sediment removal. You are prohibited from hosing or sweeping tracked-out per CGP 2.2.4.d
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  | not active | Latest report Date: |  | n/a
Notes:
Light gravel over disturbed site provides borderline cover, previously assumed to be adequate.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action