## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Comfort Suites
Location: |  |  | 1401 Woodmont SE
Site Contact Name & Agency |  |  | Nick Eveleigh |  |  |  | ESC File No. | M15E023G
|  |  | Yogash Kumar |  |  |  | NPDES Id. No. | NMR12BH30
Inspection Date: |  |  | 2019-06-11 | Start/End Time: |  | 1:00/1:30
CoA Stormwater Inspector: |  |  |  | Curtis Cherne | [9 empty] | Rain
Construction Phase: |  |  | vertical, installing utilities | [10 empty] | Clear/ Windy
Type of Inspection: |  | X | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Cloudy |  |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2019-05-10 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Hole under silt fence SW corner
2 | Grade too high against silt fence along the West side about mid-site
3 | track-out pad requires maintenance
4 | minor track-out
5 | construction and domestic waste not in an acceptable container
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | request |  | Latest report Date: |  | 2009-04-01
Notes:
a portion of the site drains out the corner with the hole under the silt fence
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Curtis Cherne PE, 505-924-3420
|  |  | ccherne@cabq.gov |  |  |  |  | 2019-06-11

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action