## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [13 empty] | Woodward and University
ESC File No. | M15E023G |  | Project Name: |  | Sunport Park - Comfort Suites | [6 empty] | R-Nicholas Eveleigh <rne@hmsgallup.com> |  | Sunport Park Hospitality-Yogash Kumar
NPDES Id. No. |  |  | Location: |  | 1401 Woodward Rd. SE | [8 empty] | 505-879-7413
2021-05-20 |  | Owner |  |  |  | Contractor | [7 empty] | Rick | 505-713-0053
Operator |  | Sunport Park Hospitality | [11 empty] | rne@hmsgallup.com
Contact name & title |  | Yogash Kumar |  |  |  | R-Nicholas Eveleigh | [5 empty] | Tim@greenglobenm.com
e-mail | [5 empty] | rne@hmsgallup.com
Contact Phone # |  | 505-879-7413 |  |  |  | 505-339-6201
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:35 PM/1:45 PM |  |  |  |  | Rain
Construction Phase: |  | Stabilization/landscaping | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 86 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Dirt area on South side does not appear to be stabilized. Provide documentation of materials used to stabilize the area, the dates applied, and the rates applied. | [9 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-06-04
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action