## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E036 |  | Project Name: |  | Sunport Appartments
NPDES Id. No. | NMR100370 |  | Location: |  | 2601 Mulberry SE
2020-08-19 |  | Property Owner |  |  |  | Contractor
Operator |  | Sunprot Apartments LLC |  |  |  | Snider Construction
Contact name & title |  | Zack Snyder |  |  |  | Gary Christiansen
Contact E-mail |  | Zsnydernm@ gmail.com |  |  |  | gchristensen@snyder-const.com
Contact Phone # |  | 505-250-8595 |  |  |  | c 505-720-8475 o 505-923-3181
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 7:30/8:40AM |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 84 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Track out in street to adjacent lot nw of Site. Remove sediment from ROW same day it occours.
2 | Construction entrance muddy. Reset and modify entrance to prevent sediment.
3 | Operator signature missing from SWPPP. All operators must sign.
4 | ESC Plan and property owner's NOI must be approved by the City for all lotsinvolved in this site.
5 | Silt fence is not at limits of disturbance along street and not embeded properly.
Yes
1.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
| Self Inspection Reports |  |  |  | Latest report Date: |  | 2020-08-17
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action