## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [11 empty] | NMR100385 |  | Snyder Construction
ESC File No. | M15E036 |  | Project Name: |  | Sunport Apartments | [6 empty] | Sunport Apartments |  | Gary Christensen
NPDES Id. No. | NMR100385 |  | Location: |  | Mulberry St. SE | [8 empty] | gchristensen@snyder-const.com
2023-08-21 |  | Owner |  |  |  | Contractor | [5 empty] | Sunport Apartments, LLC |  | 505-720-8475
Operator |  | Sunport Apartments, LLC. |  |  |  | Snyder Construction | [5 empty] | 505-872-0846
Contact name & title |  | Zach Snyder |  |  |  | Gary Christensen | [5 empty] | Zach Snyder
e-mail |  | zsnyder@snyder-const.com |  |  |  | gchristensen@snyder-const.com | [5 empty] | zsnydernm@gmail.com |  | Gaylen Barnett <Gaylen@814solutions.com>
Contact Phone # |  | 505-872-0746 |  |  |  | 505-720-8475
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9am |  |  |  |  | Rain
Construction Phase: |  | Apartment Bldg. complete, north lot disturbed | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 90 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-08-08 | [6 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP and self-inspection reports were not available on site at time of inspection. The NOI has expired, causing the SWPPP to be out-of-date had it been available. Required mitigation: You must keep a current copy of your SWPPP and your self-inspection reports at the site or at a easily accessible location, so that it can be made immediately available at the time of an on-site inspection as per CGP Parts 4.7.3 (reports) and 7.3 (SWPPP). If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site. Appendix G Part G.2 states that you have a duty to reapply if you wish to continue an activity regulated by the CGP after the expiration date. This is identical to 2017 CGP Appendix I.2.
2 | Your permit posting was missing or not visible from a safe, publicly accessible location. The sign posted onsite is missing NPDES ID#, contact information, and location of the SWPPP. Required mitigation: CGP Part 1.5 requires you to post a notice of your permit coverage so it is visible from the public road that is nearest to the active part of construction site, and it must use a font large enough to be readily viewed from a public right-of-way. It must include the NPDES ID and contact name(s) and phone number(s) for construction site information, along with URLs for contacting the EPA.
3 | Your BMPs are in need of maintenance and repair. The perimeter silt fence has holes and gaps in multiple areas and the inlet protection leading to the stormwater drainage ditch needs to be installed correctly. Required mitigation: You must ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage as per CGP Part 2.1.4.
4 | The area of land disturbances have been inactive for more than 14 calendar days (at least 19 days) and remains un-stabilized, as the site characteristics are unchanged from the previous inspection. Required mitigation: Implement an maintain stabilization measures that minimize erosion from any areas of exposed soil. You must initiate the installation of stabilization measures immediately where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days as per CGP Part 2.2.14.
In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Previous vilations include SWPPP x2, BMP x2, Posting x2, Stabilization x1
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505-924-3325)
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action