## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [11 empty] | NMR100385 |  | Snyder Construction
ESC File No. | M15E036 |  | Project Name: |  | Sunport Apartments - Staging yard | [6 empty] | Sunport Apartments |  | Gary Christensen
NPDES Id. No. | NMR10039H |  | Location: |  | 2701 Mulberry St. SE | [8 empty] | gchristensen@snyder-const.com
2023-02-22 |  | Owner |  |  |  | Contractor | [5 empty] | Sunport Apartments, LLC |  | 505-720-8475
Operator |  | Sharif Rabadi A & Samia S Star Trust |  |  |  | Snyder Construction | [5 empty] | 505-872-0846
Contact name & title |  | Sharif Rabadi |  |  |  | Gary Christensen | [5 empty] | Zach Snyder
e-mail |  | startrustofnm@yahoo.com |  |  |  | gchristensen@snyder-const.com | [5 empty] | zsnydernm@gmail.com |  | Gaylen Barnett <Gaylen@814solutions.com>
Contact Phone # |  | 505-440-6443 |  |  |  | 505-720-8475
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 1:30pm |  |  |  |  | Rain
Construction Phase: |  | Dirt pad | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Sleet |  | Temperature: ~ |  |  | 36 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-12-04 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | SWPPP not available on site at time of inspection. - Provide a scanned copy of the up-to-date SWPPP with all reports to the Storm Water Quality Section at 600 2nd St NW suite 400 - Jhughes@cabq.gov - Per CGP 4.8.2 | [9 empty] | 2021-05-03
2 | Post current CGP coverage on a sign for safe public viewing per CGP 1.5 | [10 empty] | (CGP 2.2.4)
3 | BMPs missing. Provide Silt fence around perimiter CGP 2.2.2
4 | Stabelization missing. Provide stabilization per CGP 2.2.14
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-05-17
Notes: | Called Mr Robadi, and Mr Wolff.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action