## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J12E015 |  | Project Name: |  | Bosque Antigua
NPDES Id. No. | NMR1001OG |  | Location: |  | 917 Gabaldon Dr.
2021-07-01 |  | Owner |  |  |  | Contractor
Operator |  | Las Ventanas NM, Inc,.
Contact name & title |  | Scott Ashcraft |  |  |  | Adam Romero
e-mail |  | tscott@lasventanasnm.com |  |  |  | aromero@lasventanasnm.com
Contact Phone # |  | 505-800-3377 |  |  |  | 505-440-5277
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 9:45 AM-10:10 AM |  |  |  | Rain
Construction Phase: |  | Home construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 74 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-06-28 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP not up-to-date. Update site map, activity logs, and file reports.
2 | Washout container is full. Empty washout container per CGP 2.2.3.
3 | Silt fence needs repair at West end of site. Repair/maintain silt fences.
4 | Implement temporary stabilization controls for inactive lots
5 | Implement permanent stabilization for pond areas at West end of site
6 | Waste containers are full. Empty waste containers once they are full.
7 | Provide latest self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-03
Notes: | Spoke with Grant Shanahan (superintendent) and discussed items to be mitigated. Two
homes currently being built. Four lots remain inactive and require stabilization.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action