## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E049 |  | Project Name: |  | Sagebruch Substation
NPDES Id. No. | NMR1004TS |  | Location: |  | University and Flightway (220 Sunport Blvd)
2023-09-06 |  | Owner |  |  |  | Contractor
Operator |  | Public Service Company of New Mexico |  |  |  | AECOM
Contact name & title |  | Hector Alvarez |  |  |  | Bill Haynes
e-mail |  | hector.alvarez@pnmresources.com |  |  |  | bill.haynes@aecom.com
Contact Phone # |  | 505-241-2028 |  |  |  | 865-394-8129
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 430pm |  |  |  | Rain
Construction Phase: |  | earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP Certification and Delegation of Authority needs to be signed which is a violation of CGP Part 7.2.10. A copy of the 2022 CGP was not available to the City Inspectors at the time of inspection in violation of CGP Part 7.2.11.c as the inspectors had no ability to view the USB drive provided with the SWPPP. Verification of current training for the Stormwater Team and/or stormwater inspectors were not located in the SWPPP in violation of CGP Parts 6 and 7.2.2. Required mitigation: CGP Appendix G, Part G.11.2 states that the SWPPP (and any modifications), site inspection reports, corrective action log, and any other compliance documentation must be signed by a duly authorized representative, which must have the written authorization signed and dated by the operators included in the SWPPP. Once the Delegation of Authority is signed, the representative can sign for the operators to satifsy the requirements of CGP Part 7.2.10 and any other signature needs, with the exception of the Notice of Termination (Note that the Delegation of Authority cannot be to a subcontractor or third-party (E2RC)). While the EPA permits electronic records, the fact sheet for CGP Part 4.7.2 states that the electronic access needs to be using hardware and software available at the site in order to satisfy CGP Part 7.2.11.c. CGP Part 7.2.2 states the requirement to identify personnel and to include verification that each member of the Stormwater Team and stormwater inspectors have received training required in CGP Part 6 by including documentation that their certification or liscense is still current.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-08-30
Notes:
Inspection was for SWPPP and brief drive-around.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action