## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [11 empty] | NMR100385 |  | Snyder Construction
ESC File No. | M15E054 |  | Project Name: |  | Veterans Integration Center | [6 empty] | Sunport Apartments |  | Gary Christensen
NPDES Id. No. | NMR1005M1 |  | Location: |  | 2701 Mulberry St. SE | [8 empty] | gchristensen@snyder-const.com
2023-05-15 |  | Owner |  |  |  | Contractor | [5 empty] | Sunport Apartments, LLC |  | 505-720-8475
Operator |  | NM Vertran Integration Centers |  |  |  | Jaynes | [5 empty] | 505-872-0846
Contact name & title |  | Jerry Becker | [9 empty] | Zach Snyder
e-mail |  | jerry@steamaticnm.com | [9 empty] | zsnydernm@gmail.com |  | Gaylen Barnett <Gaylen@814solutions.com>
Contact Phone # |  | 505-833-7766
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4:30pm |  |  |  |  | Rain
Construction Phase: |  | Apartment Bldg complete, north lot dirt. | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | BMPs were completely missing from the site and sediment from your site has blown into Mulberry St. Your BMPs (silt Fence) must be constructed, and sediment picked up and removed from street. | [9 empty] | 2021-05-03
2 | SWPPP not available on site at time of inspection, so it couldn't be checked to see if it is up-to-date. 6. The SWPPP including Self Inspection Reports and Corrective Action Reports must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
3 | Stabilization was missing - You must begin appying seed and hydromulch within 14 days no any area where construction activities cease for 14 days or more, and you must complete the seed and mulch in 14 days or less per CGP 2.2.14. You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied.
4
5
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | Yes
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | none
Notes: | Jerry Becker's phone 505-833-7766 wasn't in service 5/16/23. He is the Point of Contact.
The first notice of these violations was sent 2/27/23 before NMVIC purchased this site. A reminder was sent with plan review comments on 5/4/23. This report is a Level 1 notice per Escalation Process.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action