## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E054 |  | Project Name: |  | Veterans Integration Center
NPDES Id. No. | NMR1005M1 |  | Location: |  | 2701 Mulberry St SE
2025-01-28 |  | Owner |  |  |  | Contractor
Operator |  | NM Veteran Integration Centers |  |  |  | Hart Construction
Contact name & title |  | Jerry Becker
e-mail |  | jerry@steamaticnm.com
Contact Phone # |  | 505-991-4708
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 315pm |  |  |  | Rain
Construction Phase: |  | south addition | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 57 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting - The permit coverage posting was missing from the site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site.
2 | SWPPP - The SWPPP and self-inspection reports were unavailable at the time of the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
3 | BMPs - The perimeter silt fence needs maintenance around the south and west sides of the property in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage per CGP Part 2.1.4.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The general contractor has changed from Jaynes Corporation to Hart Construction. Hart Construction will need to include their NOI in the SWPPP.
The concrete washout pit is full and needs to be emptied before it can be used again.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action