## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M15E054 |  | Project Name: |  | Veterans Integration Center
NPDES Id. No. | NMR1005M1 |  | Location: |  | 2701 Mulberry St SE
2025-12-02 |  | Owner |  |  |  | Contractor
Operator |  | NM Veteran Integration Centers |  |  |  | Hart Construction
Contact name & title |  | Jerry Becker
e-mail |  | jerry@steamaticnm.com
Contact Phone # |  | 505-991-4708
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | south addition interiors | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The following information is missing from the SWPPP, which needs modification in violation of several CGP Parts. The operators need to be updated to identify the new operator, Hart Construction (CGP Part 7.2.1). The Stormwater Team needs to be updated to identify the personnel (by name and position) responsible for CGP compliance, along with their individual responsibilities (CGP Part 7.2.2). The SWPPP needs to be certified by each operator's signatory (CGP Part 7.2.10). The Notices of Intent (NOIs) for each operator need to be included in the SWPPP (CGP Part 7.2.11). The SWPPP, including the SWPPP Map, needs to be amended to reflect the current conditions on the ground (CGP Part 7.4.1). Copies of all self-inspection reports need to be available for an on-site inspection (CGP Part 4.7.3). Required mitigation: Include a list of all other operators who will be engaged in construction activities at the site, and the areas of the site over which each operator has control per CGP Part 7.2.1. Identify the personnel (by name and position) that you have made part of the stormwater team pursuant to CGP Part 6.1, as well as their responsibilities per CGP Part 7.2.2. Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11. You must include a copy of your NOI submitted to the EPA along with correspondence exchanged between you and the EPA related to coverage under this permit per CGP Part 7.2.11.a. You must modify your SWPPP, including the site map(s), within seven days whenever new operators become active in construction activities on your site, or you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1.a. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 6/25/2025*
Notes:
The SWPPP is in the main building with the Facilities Manager. The general contractor has changed from Jaynes Corporation to Hart Construction.
*The latest inspection report on-site was dated 6/25/2025, and the latest inspection performed was on 11/27/2025.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action