## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR1003G0
ESC File No. | M16E024N |  | Project Name: |  | Orion Center | [5 empty] | Orion Center; SEC of Gibson and Girard
NPDES Id. No. | NMR1003G0 |  | Location: |  | SEC of Gibson and Girard
2021-06-09 |  | Owner |  |  |  | Contractor |  |  |  |  | Hensel Phelps - Raul Velez
Operator |  | Hensel Phelps | [8 empty] | 602-471-4637
Contact name & title |  | Raul Velez | [8 empty] | rvelez@henselphelps.com
e-mail |  | rvelez@henselphelps.com
Contact Phone # |  | 602-471-4637 | [8 empty] | E2RC
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:25 AM-12:05 PM |  |  |  | Rain
Construction Phase: |  | infrastructure/staging/stockpiling | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Sediment in the streets. Sweep and remove sediment from the streets daily. | [9 empty] | 2021-05-03
2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | No activity on the East side of Girard. The lot on the West side of Girard is being used for
stockpiling. The company doing the work is IPR, LTD. Mike Daniels is the main contact. I spoke with
Frank Clark at the site. He said this lot has been used for stockpiling before. There are no BMPs in
this area. THIS SITE IS UNDER AVIATION'S INSPECTION AND CONTROL.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action