## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M21E015B |  | Project Name: |  | Volterra - Unit 3
NPDES Id. No. | NMR1000AZ |  | Location: |  | Juan Tabo and Cavalcade Dr.
2021-04-19 |  | Owner |  |  |  | Contractor
Operator |  | LGI Homes |  |  |  | LGI Homes
Contact name & title |  | Ron Rieger |  |  |  | Dale Works
e-mail |  | rrieger@lgihomes.com |  |  |  | Dale.Works@lgihomes.com
Contact Phone # |  | 505-934-3116 |  |  |  | 505-379-3822
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 12:25 PM/1:00 PM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-02-22 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Maintain/replace inlet protection
2 | Clean trackout and remove dirt from sidewalks
3 | Remove and dispose of washout
4 | Secure trash bins and provide covers
5 | Clean washout area
6 | Repair/replace silt fences
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | last week
Notes: | Spoke with Dale (Foreman). He emailed Superior earlier today regarding fixing the inlet
protection controls. He confirmed that the last self-inspection was conducted last week.
We discussed the issues above that need mitigation. SWPPP is held at their office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action