## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Juan Tabo Hills
Location: |  |  | Juan Tabo Hills West - bfeeney@rayleehomes.com
Site Contact Name & Agency |  |  | Sherri Repiechowski |  |  |  | ESC File No. | M21E018
|  |  | sherri@paulallenhomes.net |  |  |  | NPDES Id. No. | NMR1001A4
Inspection Date: |  |  | 2022-08-19 | Start/End Time: |  | 11am
CoA Stormwater Inspector: |  |  |  | James Hughes | [9 empty] | Rain
Construction Phase: |  |  | landscaping | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Cloudy |  |  | Temperature: ~ |  |  | 86 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2022-08-21 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP was available but not up-to-date. The SWPPP certifier and the NOI certifier should be the same person, then the operator cvan deligate to an employee for all other signatures on the SWPPP. Sherii signed the NOI but not the SWPPP, delegation of authority, or any of the self-inspection reports. Either change the NOI or the SWPPP signatures and make sure that they meet the criteria in CGP appendix I.11.
2 | The stabilization of the slopes in the HOA Tracts on the south and east side of the site doesn’t satisfy the final stabilization criteria in the CGP at Part 2.2.14 yet. so BMPs must remain to keep sediment out of the streets, and inspection must continue until the site satisfies the CGP criteria.
3 | Large piles of sediment have been harvested at the toe of the slope in the east HOA Tract and erosion is occurring at the toe of the slope in the HOA tract on the south side of the site. Erosion should be prevented with rip-rap and sediment should be removed from the channel at the toe off the slope on the east side of the site. All of the slopes need to be stabilized with a combination of seed and rock mulch per the draft City Standard Specification 1013 attached or equal.
4 | Portions of the HOA tract (linier park) along the Tijeras Arroyo and the disturbed area in the Tijeras arroyo still don’t satisfy the stabilization criteria either.
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports | [5 empty] | Latest report Date: |  | 2022-07-25
Notes: | Deligation of authority to Bob Feeney is missing and Bob certified the SWPPP.
The NOI and SWPPP certification should agree. The final Stabilization criteria isn't satisfied so BMPs and inspectopn reports must continue.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | James Hughes 505-924-3420
|  |  | Jhughes@cabq.gov |  |  |  |  | 2022-08-19

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action