## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Juan Tabo Hills Estates
Location: |  |  | Juan Tabo and Tijeras Arrojo
Site Contact Name & Agency |  |  | Bob Feeney |  |  |  | ESC File No. | M21E018
|  |  | Raylee Homes |  |  |  | NPDES Id. No. | NMR1001A4
Inspection Date: |  |  | 5.23.19 | Start/End Time: |  | 1:00 |  | 3:00
CoA Stormwater Inspector: |  |  |  | Curtis Cherne | [9 empty] | Rain
Construction Phase: |  |  | constructing scour wall | [10 empty] | Clear/ Windy
Type of Inspection: |  | X | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear/ Windy |  |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2019-05-10 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | numerous wash-outs
2 | rock filter downstream of pond is full and is being bypassed on north end
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports | [5 empty] | Latest report Date: |  | 2019-05-10
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Curtis Cherne PE, 505-924-3420
|  |  | ccherne@cabq.gov |  |  |  |  | 5.23.19

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action