## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Juan Tabo Hills Estates
Location: |  |  | Juan Tabo & Tijeras
Site Contact Name & Agency |  |  | Kevin Griffin - DR Horton |  |  |  | ESC File No. | M21E018H
|  |  | kgriffin@drhorton.com |  |  |  | NPDES Id. No. | NMR1001Y2
Inspection Date: |  |  | 2019-08-12 | Start/End Time: |  | 1230/1250hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [8 empty] | Rain
Construction Phase: |  |  | home construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  | 84* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [12 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
no issues observed with this inspection
Please provide latest SWPPP self-inspection report
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2019-08-12

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action