## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M21E018H |  | Project Name: |  | Juan Tabo Hills Estates
NPDES Id. No. | NMR1001Y2 |  | Location: |  | Juan Tabo and Pocono
2021-11-19 |  | Owner |  |  |  | Contractor
Operator |  | D.R. Horton, Inc.
Contact name & title |  | Joseph Cordero |  |  |  | joseph
e-mail |  | JACORDERO@DRHORTON.COM'
Contact Phone # |  | 505-991-5266
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  |  | Rain
Construction Phase: |  | Vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 39 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-10-01 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout on the ground. Direct wash water from concrete, paint, and stucco into a leak-proof container per CGP 2.3.4. Remove and dispose of hardened concrete with other waste per CGP 2.3.3
2 | NPDES coverage was not posted. 7. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP 1.5.
3 | The NOI is not Up-to-date & SWPPP was not available onsite. The SWPPP must be kept up-to-date and available onsite per CGP 7.1. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3. | [10 empty] | kgriffin@drhorton.com
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-11-25
Notes: | Only 5 lots still under construction. Kevin Griffin no longer with DR Horton, but NOI
not updated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes 505-924-3420
Jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action