## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M21E018_R |  | Project Name: |  | Raylee Homes at Juan Tabo Hills Estates
NPDES Id. No. | NMR1002FM |  | Location: |  | Popejoy, Rodey, and Sunset
2022-08-19 |  | Owner |  |  |  | Deligated Authority
Operator |  | SLG Holdings, and TJT Group, LTD. |  |  |  | Raylee Homes field super
Contact name & title |  | Jeff Grady |  |  |  | Sal Chavez
e-mail |  | jgrady@rayleehomes.com
Contact Phone # |  | 505-975-7544 |  |  |  | 975-1505
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 1:30pm |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-08-21 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Remove inlet protection from all inlets downstream of the site in Rocky Top and clean sediment from streets and sidewalks. Keep sediment out of street!
2 | The cutback swale isn't eneough. Keep the sediment out of the street by adding silt fence at low corner of each lot 15' x 15'.
3 | Minor washout on nw lot at SWPPP sign. Clean up and add washout containers.
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2022-07-14
Notes: | 2017 Noi updated to 2022
SWPPP map signatures and deligation OK. SLG (aka Raylee) is both the contractor and owner
and certified the SWPPP twice, once as each. Deligation to Sal Chavez (field Super) is in order.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes - 505-924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action