## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M21E018_T |  | Project Name: |  | Volterra - Juan Tabo Hills
NPDES Id. No. | NMR1003L0 |  | Location: |  | 11404 Rock Squirrel Ave SE
2021-04-06 |  | Owner |  |  |  | Contractor
Operator |  | Twilight Homes |  |  |  | Twilight Homes
Contact name & title |  | Tim Mcnaney |  |  |  | Tim Mcnaney
e-mail |  | tmcnaney@twilighthomes.com |  |  |  | tmcnaney@twilighthomes.com
Contact Phone # |  | 505-975-1154 |  |  |  | 505-975-1154
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 2:55 PM/3:25 PM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Complaint |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear/ Windy |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-02-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No violations observed.
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-06-30
Notes: | Inspection conducted as a result of a complaint that a silt fence was blocking an inlet.
The storm inlets had wattles protecting the inlets that were properly installed. No silt fence was
observed.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action