## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N08E006F2,3,5 |  | Project Name: |  | Aspire Subdivision Units 1-4
NPDES Id. No. | NMR100490 |  | Location: |  | 118th St and Colobel Ave SW
2024-07-16 |  | Owner |  |  |  | Contractor
Operator |  | DR Horton
Contact name & title |  | Joseph Cordero
e-mail |  | jacordero@drhorton.com
Contact Phone # |  | 505-991-5266
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10am |  |  |  | Rain
Construction Phase: |  | Home Construction & Final Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-06-30 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | PO | [9 empty] | 2021-04-28
1 | The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and a copy of all inspection reports at the site or at an easily accessible location where they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. | [9 empty] | 2021-05-03
2 | The permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP Part 1.5.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | N/A
Notes:
The doc-box was empty and on the ground at the time of inspection. Ensure that the SWPPP and permit coverage posting has proper contact information and is up-to-date. All perimeter areas for Units 1 and 2 have been stabilized.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action