## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N08E006F |  | Project Name: |  | Aspire Subdivison Unit 1 | [5 empty] | Aspire Subdivision Unit 1; 118th St. and Colobel Ave. |  |  | Jeremiah Priest
NPDES Id. No. | NMR1003LW |  | Location: |  | 118th St. and Colobel Ave. | [5 empty] | NMR1003LW
2021-07-08 |  | Owner |  |  |  | Contractor
Operator |  | Heritage Trails Development 1, LLC |  |  |  | Salls Brothers |  |  |  |  | Heritage Trails Development 1, LLC; Garrett Price |  | Scott Stephen
Contact name & title |  | Garrett Price |  |  |  | M. Dyer |  |  |  |  | 505-243-3949 |  | 'ssteffen@priceldg.com'
e-mail |  | gprice@priceldg.com |  |  |  | mdyer@sallsbrothers.com |  |  |  |  | gprice@priceldg.com
Contact Phone # |  | 505-243-3949 | [8 empty] | Green Globe
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 10:05 AM-10:30 AM |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-07-06 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Accumulated tumbleweeds. Remove tumbleweeds that have accumulated on site. | [9 empty] | 2021-05-03
2 | Domestic waste accumulated at SE corner. Remove waste and place in an approved waste container. | [9 empty] | 2021-05-31
3 | SWPPP requires signatures. Owner/contractor needs to sign forms for SWPPP team, delegation of authority, and subcontractor agreements.
4 | Latest self-inspection report not provided upon last request.
5 | NOI posting is not in a location accessible to the public. Move posting near the construction entrance so that it is clearly visible to the public.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | SWPPP is kept in a lock box behind the posting sign. Site map has been updated and some
self-inspection reports are included in the SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action