## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N08E006F2 |  | Project Name: |  | Aspire Subdivision Unit 1 Work Order
NPDES Id. No. | NMR1003RD |  | Location: |  | 11000 Colobel Ave NW
2021-01-22 |  | Owner |  |  |  | Contractor
Operator |  | Heritage Trails Development, LLC
Contact name & title |  | Garret Price |  |  |  | Scott Stephen
e-mail |  | gprice@priceldg.com |  |  |  | ssteffen@priceldg.com
Contact Phone # |  | 304-8473 |  |  |  | 243-3949
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 10am |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2021-02-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
construction not started yet. Reason for inspection is to check stabilization from previous 2004 development. The ground cover is more than 70% of natural undisturbed cover.
First 100' Transect is offsite 300' west of the intersection of 118th St./Amole Mesa Ave SW. Grass is conspicuously absent, only sage (3 pnt) and litter (3 pnt) Oak ?dead (1pnt)
7 pnt cover/34 pnt total= 20% cover
Second 100' transect in center of 80 acres site sampling points every 3' - 34 points total Grass (3pnt) liter 1(pnt) sage (1) = 15% cover which is 75 % of natural undisturbed.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action