## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [13 empty] | Kevin Griffin - DR Horton
ESC File No. | N08E006F3 WO |  | Project Name: |  | Aspire Subdivison Unit 2-4 | [5 empty] | Aspire Subdivision Unit 1; 118th St. and Colobel Ave. |  |  | 505-206-8226
NPDES Id. No. | NMR1003RV/NMR1003RD |  | Location: |  | 118th St. and Colobel Ave. | [5 empty] | NMR1003RV/NMR1003RD |  |  | ktgriffin@drhorton.com
2023-11-22 |  | Owner |  |  |  | Contractor
Operator |  | Heritage Trails Development 1, LLC | [8 empty] | Heritage Trails Development 1, LLC; Garrett Price |  | Scott Stephen
Contact name & title |  | Garrett Price | [8 empty] | 505-243-3949 |  | ssteffen@priceldg.com' | mdyer@sallsbrothers.com
e-mail |  | gprice@priceldg.com | [8 empty] | gprice@priceldg.com
Contact Phone # |  | 505-243-3949 | [8 empty] | Green Globe
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 9AM |  |  |  | Rain
Construction Phase: |  | Unit 2 Infrastructure Complete & Sold to DR Horton. Unit 3 & 4 is swale and ponds. | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-11-19 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The NOI (NMR1003RV) expired 2/16/22 and the new property owner is Success Land Holdings LLC (attn PLDG). The NOI is Missing from the SWPPP. | [9 empty] | 2021-05-03
2 | BMPs the west bank of the unit 2 diversion swale is damaged next to unit 2. | [9 empty] | 2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2023-10-20
Notes: | The SWPPP is located in a lock box attached to the posting.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action