## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N08E006F3 |  | Project Name: |  | Aspire Subdivision Unit 1 & 2 Houses
NPDES Id. No. | NMR100490 |  | Location: |  | 11000 Colobel Ave NW
2023-11-22 |  | Owner |  |  |  | Contractor
Operator |  | DR Horton
Contact name & title |  | Todd Warmkessel
e-mail |  | twarmkessel@drhorton.com
Contact Phone # |  | 225-4760
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:30 |  |  |  | Rain
Construction Phase: |  | only 2 lots left in Unit 1 and 20 houses started in Unit 2 | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-11-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
The Posting shows Joseph Cordero and NMR1003LW both wrong. Required Mitigation: Update Posting to Todd Warmkessel at 505-225-4760 and NMR100490.
The SWPPP Map should be updated to add check dams or silt fence on each side lot line in the cut-back swales on streets with 2% or more slope. Cutbacks should not be shown where sidewalk is already constructed. The map must also show the Diversion Swale and Sediment Basins on the neighboring property that serve these lots. Consider using approved G&D as base. Deligation to Todd Warmkessel is missing.
BMPs the diversion swale on the adjacent property has a breach in the bank that needs to be repaired.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2023-10-20
Notes:
Joseph Cordero signed Original NOI and SWPPP then switched to Todd Warmkessel in 2023.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action