## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N08E006F5 |  | Project Name: |  | Aspire Subdivision Units 3 & 4
NPDES Id. No. | NMR100490 |  | Location: |  | 10600 Amole Mesa Ave SW
2025-02-04 |  | Owner |  |  |  | Contractor
Operator |  | DR Horton |  |  |  | DR Horton
Contact name & title |  | Joseph Cordero |  |  |  | Todd Warmkessel
e-mail |  | jacordero@drhorton.com |  |  |  | twarmkessel@drhorton.com
Contact Phone # |  | 505-991-5266 |  |  |  | 505-225-4760
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-01-24
Notes:
The concrete washout area needs to be cleaned up.
The Delegation of Authority page needs to be completed for the superintendant to sign the inspection reports.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action