## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N08E006F5 |  | Project Name: |  | Aspire Subdivision Units 3 & 4
NPDES Id. No. | NMR100490 |  | Location: |  | 10600 Amole Mesa Ave SW
2026-02-02 |  | Owner |  |  |  | Contractor
Operator |  | DR Horton |  |  |  | DR Horton
Contact name & title |  | Joseph Cordero
e-mail |  | jacordero@drhorton.com
Contact Phone # |  | 505-991-5266
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Verticals, foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Washout - The washout pit is full, and the area is covered in waste concrete and concrete washout in violation of CGP Part 2.3.4. Required mitigation: Direct wash-water into a leak-proof container or a leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or otherwise be disposed of on the ground. Remove and dispose of hardened concrete waste consistent with your handling of other construction wastes.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2026-01-22
Notes:
The SWPPP is in a doc-box mounted on the back of the posting in front of the construction office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action