## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N09E013_Dask |  | Project Name: |  | Los Diamantes Subdivision Infrastructure
NPDES Id. No. | NMR1000L3 |  | Location: |  | 9800 Gibson Blvd SW
2021-01-27 |  | Owner |  |  |  | Contractor
Operator |  | 98th St , LLC
Contact name & title |  | Jimmy Daskalose
e-mail |  | jd@onepayhr.com
Contact Phone # |  | 872-1700
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4:30pm |  |  |  | Rain
Construction Phase: |  | infrastructure complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-02-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The NPDES coverage needs posted near the north pond. The SWPPP location must also be identified on the sign.
2 | Stabelization of the north pond failed. It needs to be weeded, and stabelized with seed and mulch per CGP 2.2.14.b..
3 | Self inspection is required every 2 weeks until the final stabilization criteria (CGP 2.2.14.b) is satisfied please provide the latest report.
4 | Minor silt fence repair is recommended along the east side of the pond.
5 | Onsite pond must satisfy the Final Stabelization Criteria.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
Notes:
Contractor filed NOT 9/6/2019 without sucessor operator or final stabilization, which
violates CGP 8.2. The property owner paid for plans and is an operator but failed to file NOI.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action