## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N09E014 |  | Project Name: |  | Desert Sands
NPDES Id. No. | NMR1000BE |  | Location: |  | 3000 98th St SW
2023-06-02 |  | Owner |  |  |  | Contractor
Operator |  | Salazar |  |  |  | LGI Homes
Contact name & title |  | Eddie Loven |  |  |  | Greg Mayfield & Edddie Loven
e-mail |  | Eloven@lgihomes.com |  |  |  | greg.mayfield@lgihomes.com
Contact Phone # |  | 991-0807 |  |  |  | 970-640-1786
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | infrastructure complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The pond is covered with gravel satisfying CGP 2.2.14.C.ii, Please remove all Silt fence remanants.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | ?
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action