## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | 98th st and colobel desert sands
ESC File No. | N09E014 |  | Project Name: |  | Desert Sands | [6 empty] | dale.works@lgihomes.com
NPDES Id. No. | NMR1000BE |  | Location: |  | 3000 98th Street SW | [5 empty] | LGI Homes-Mark Kaberlein
2021-06-09 |  | Owner |  |  |  | Contractor |  |  |  |  | 480-294-1768 | Eddie Loven
Operator |  | LGI Homes |  |  |  | LGI Homes | [5 empty] | LGI Homes
Contact name & title |  | Eddie Loven | [9 empty] | Eloven@lgihomes.com
e-mail |  | Eloven@lgihomes.com
Contact Phone # |  | 505-991-0807
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 8:50 AM-9:00 AM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 73 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Pond is not stabilized. Implement stabilization controls per CGP 2.2.14b | [9 empty] | 2021-05-03
2 | No posting of NOI permit coverage. Post NOI permit coverage in a location clearly visible to the public. | [9 empty] | 2021-05-31
3 | No sediment control BMP (silt fence) installed. Install BMP during stabilization process.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-03-05
Notes: | Homes construction is completed. Significant erosion on slopes of pond. Requested actions
from last inspection dated 1/27/2021 have not been implemented.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action